## OrangeHRM_Tasks
Test Strategy Document
Test Strategy Document Title | Tester_Name | Modules | Decription | Tester_Name | Module_TestCase_Count | High_Priority
Chapter 1: Introduction | Pulkit | PIM | Add an employee, Delete an employee,Search an employee | Siddhant | 16 | 11
Chapter 2: Scope of Testing | Shweta | Leave | Apply leave, My leave, approve or reject leave | Shweta | 17 | 10
Chapter 3: Automation Script Development Process | Shweta | Time | Enter time w.r.t Project, view time , Approve and Reject time | Saba | 15 | 7
Chapter 4: Test Approach | Siddhant | Dashboard | Verify and view the actions performed , Notification test | Pulkit | 47 | 18
Chapter 5: Risk Management | Saba | Login | Verify able to login using valid credentials | Pulkit | 5 | 4
Chapter 6: Defect Management | Saba
Final Test Strategy Document Created By | Shweta | Admin
|  | Modules | Tester_Name
|  | PIM | Siddhant
Test Planning Document |  | Leave | Shweta
Test Planning Document Title | Tester_Name | Time | Saba
|  | Dashboard | Pulkit
Employee
|  | Modules | Tester_Name
|  | Leave | Shweta
|  | Time | Saba
|  | Dashboard | Pulkit
|  | PIM | Siddhant

## Time
TC No | Test Description | Step Number | Test Step | Validation | Priority
Time_EMP_1 | Employee to record Punch In | Step 1 | Employee to login with the valid credentials |  | High
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to attendence->Punch In/Punch Out
|  | Step 4 | Set the time and click on In button | Punched in time should display
Time_EMP_2 | Employee to record Punch Out | Step 1 | Employee to login with the valid credentials |  | High
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to attendence->Punch In/Punch Out
|  | Step 4 | Set the time and click on out button | Punch out to happen successfully
Time_EMP_3 | Employee to view the punching record | Step 1 | Employee to login with the valid credentials |  | High
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to attendence->My Records | Employee Punch In and Punch Out record should display
Time_EMP_4 | Employee to Enter/record the time sheet 8 hrs | Step 1 | Employee to login with the valid credentials |  | High
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Click on Edit button
|  | Step 4 | Select a valid project
|  | Step 5 | Select and activity
|  | Step 6 | Enter time 8hr in each block as per the date | To verify if Employee can enter 8hr daily
|  | Step 7 | Click on save button | Record should be saved but not in submitted
|  | Step 8 | Click on Submit button | The status should be now in submitted
Time_EMP_5 | Employee to Enter/record the time sheet more than 24 hrs a day | Step 1 | Employee to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Click on Edit button
|  | Step 4 | Select a valid project
|  | Step 5 | Select and activity
|  | Step 6 | Enter time 24hr in each block as per the date | To verify if Error appears
|  | Step 7 | Click on save button | Unable to save the record
Time_EMP_6 | Employee to Enter/record the time sheet less than 0 hrs a day | Step 1 | Employee to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Click on Edit button
|  | Step 4 | Select a valid project
|  | Step 5 | Select and activity
|  | Step 6 | Enter time in minus hr in each block as per the date | To verify if Error appears
|  | Step 7 | Click on save button | Unable to save the record
Time_ADM_1 | Admin to record Punch In | Step 1 | Admin to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to attendence->Punch In/Punch Out
|  | Step 4 | Set the time and click on In button | Punched in time should display
Time_ADM_2 | Admin to record Punch Out | Step 1 | Admin to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to attendence->Punch In/Punch Out
|  | Step 4 | Set the time and click on out button | Punch out to happen successfully
Time_ADM_3 | Admin to view the punching record | Step 1 | Admin to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to attendence->My Records | Admin Punch In and Punch Out record should display
Time_ADM_4 | Admin to view the employee record | Step 1 | Admin to login with the valid credentials |  | High
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to attendence->Employee Records
|  | Step 4 | Search with the employee name and Date
|  | Step 5 | Click on view button | Admin should view the correct time details of the searched employee
Time_ADM_5 | Admin to Enter/record the time sheet for him | Step 1 | Admin to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to timesheet->My Timesheet and edit
|  | Step 4 | Select a valid project
|  | Step 5 | Select and activity
|  | Step 6 | Enter time 8hr in each block as per the date | To verify if Employee can enter 8hr daily
|  | Step 7 | Click on save button | Record should be saved but not in submitted
|  | Step 8 | Click on Submit button | The status should be now in submitted
Time_ADM_6 | Admin to Enter/record the time sheet for Employee | Step 1 | Admin to login with the valid credentials |  | High
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to timesheet->Employee Timesheet
|  | Step 4 | Serch with the Employee Name
|  | Step 5 | Click on create timesheet button and then Edit
|  | Step 6 | Select a valid project
|  | Step 7 | Select and activity
|  | Step 8 | Enter time 8hr in each block as per the date | To verify if Employee can enter 8hr daily
|  | Step 9 | Click on save button | Record should be saved but not in submitted
|  | Step 10 | Click on Submit button | The status should be now in submitted
|  | Step 11 | From the below 2 options Admin can Approve/Reject the time sheet | Timesheet should be approved or rejected
Time_ADM_7 | Admin Reporting:Project Report | Step 1 | Admin to login with the valid credentials |  | High
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to Report->Project Report
|  | Step 4 | Select project name from the LOV
|  | Step 5 | Enter date range
|  | Step 6 | Click on view button | Report should display with valid data
Time_ADM_8 | Admin Reporting:Employee Report | Step 1 | Admin to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to Report->Employee Report
|  | Step 4 | Enter Employee Name
|  | Step 5 | Enter date range(optional)
|  | Step 6 | Click on view button | Report should display with valid data
Time_ADM_8 | Admin Reporting:Attendence Summary Report | Step 1 | Admin to login with the valid credentials |  | Medium
|  | Step 2 | Click on Time tab from the left grid
|  | Step 3 | Navigate to Report->Attendence Summary Report
|  | Step 4 | Enter Employee Name
|  | Step 5 | Enter date range(optional)
|  | Step 6 | Click on view button | Report should display with valid data

## Leave
TC No | Test Description | Step Number | Test Step | Validation | Expected Result | Priority
Leave_Admin_1 | Verify Admin able to assign/allocate leave for a Specific Employee. | Step1 | Admin Login with Valid Credentials | Confirm that the employee's leave balance is updated correctly, reflecting the assigned leave. | The admin should be able to successfully assign or allocate leave for the specific employee for the selected leave type and duration. Upon verification, the employee's leave balance should reflect the assigned leave accurately. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Entitlements menu and select add Entitlements
|  | Step4 | Select the specific employee for whom leave is to be assigned.
|  | Step5 | Choose the leave type to be assigned
|  | Step6 | Set the allocation date or leave period.
|  | Step7 | Specify the number of leave days to be assigned
|  | Step8 | Click on the Save button
Leave_Admin_2 | Verify Employee Leave Entitlements by Employee Name, Leave Type, and Leave Period | Step1 | Admin Login with Valid Credentials | Confirm that the displayed entitlements match the expected values for the selected criteria. | The system should correctly retrieve and display the leave entitlements for the specified employee, leave type, and leave period. The displayed entitlements should be accurate and align with the criteria provided for verification. | Medium
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Entitlements menu and select Employee Entitlements
|  | Step4 | Enter the employee's name.
|  | Step5 | Choose the specific leave type
|  | Step6 | Enter the leave period, including the start date and end date.
|  | Step7 | Click on the search button.
Leave_Admin_3 | Verify Admin Allocating Leave for Multiple Employees | Step1 | Admin Login with Valid Credentials | Confirm that the employee's leave balance is updated correctly, reflecting the assigned leave. | The admin should be able to successfully assign leave to multiple employees simultaneously for the selected leave type,location and duration. Upon verification, the leave balances of each selected employee should reflect the assigned leave accurately. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Entitlements menu and select add Entitlements
|  | Step4 | Select multiple employees checkbox
|  | Step5 | Select Location from location menu list
|  | Step6 | Select subtype form subtype menu list
|  | Step7 | Choose the leave type to be assigned
|  | Step8 | Enter the leave period, including the start date and end date.
|  | Step9 | Specify the number of leave days to be assigned
|  | Step10 | Click on the Save button
Leave_Admin_4 | Verify User Can Configure Leave Types | Step1 | Admin Login with Valid Credentials | Check if the newly configured leave type is displayed in the list of available leave types. | After configuration, the new leave type should be saved and displayed correctly in the list of available leave types. | Medium
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Configure menu and select Leave Types
|  | Step4 | Click on Add button to add new leave type
|  | Step5 | Enter the New leave type name
|  | Step6 | Click on the Save button
|  | Step7 | Choose the leave type to be assigned
|  | Step8 | Enter the leave period, including the start date and end date.
|  | Step9 | Specify the number of leave days to be assigned
|  | Step10 | Click on the Save button
Leave_Admin_5 | Verify User Can Configure Holidays List | Step1 | Admin Login with Valid Credentials | Confirm that the holiday details, including its name and date, match the entered information. | After configuration, the new holiday should be saved and displayed correctly in the list of holidays for the relevant year. | Medium
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Configure menu and select Holidays
|  | Step4 | Click on Add button to add new Holiday
|  | Step5 | Enter the New Holiday name
|  | Step6 | Enter the date
|  | Step7 | Select Full day or Half day
|  | Step8 | Click on the Save button
|  | Step9 | Search the Holiday to be assigned
|  | Step10 | Enter From and To date
|  | Step11 | Click on the search button.
Leave_Admin_6 | Verify Leave List Displayed Based on "From Date," "Show Leave with Status," and "Leave Type" Selections | Step1 | Admin Login with Valid Credentials | Confirm that the displayed leave records match the selected filter criteria. | The system should successfully display the leave list based on the selected filter criteria. The displayed leave records should accurately match the filter selections for "From Date," "Show Leave with Status," and "Leave Type." | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Leave List Tab
|  | Step4 | Enter a specific "From Date" to filter leave records based on the starting date.
|  | Step5 | Select a particular "Show Leave with Status" option (e.g., Approved, Pending, Rejected) to filter leave records by status.
|  | Step6 | Choose a specific "Leave Type"
|  | Step7 | Click on Search button
Leave_Admin_7 | Verify Error Message for Missing "Show Leave with Status" Selection | Step1 | Admin Login with Valid Credentials | Confirm that the error message is clear and informs the user about the missing selection. | The error message should be informative and guide the user to make a selection. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Leave List Tab
|  | Step4 | Ensure that no value is selected in the "Show Leave with Status"
Leave_Admin_8 | Verify Leave List Displayed with Multiple Leave Status Filters and Date Range | Step1 | Admin Login with Valid Credentials | Confirm that the displayed leave records match the selected filter criteria, including status and date range. | The system should successfully display the leave list based on the selected multiple "Show Leave with Status" options and the specified date range. The displayed leave records should accurately match the selected filter criteria, including status and date range. | Medium
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Leave List Tab
|  | Step4 | Enter a specific "From Date" to filter leave records based on the starting date.
|  | Step5 | Select multiple "Show Leave with Status" options
|  | Step6 | Click on Search button
Leave_Admin_9 | Verify Employee Leave List Filtered by Name, Leave Status, and Date Range | Step1 | Admin Login with Valid Credentials | Check that leave records are accurately filtered by the employee's name, leave status, and the specified date range. | The system should successfully display the employee leave list based on the selected employee name, leave status, and date range. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Leave List Tab
|  | Step4 | Enter a specific "From Date" to filter leave records based on the starting date.
|  | Step5 | Select a particular "Show Leave with Status" option (e.g., Approved, Pending, Rejected) to filter leave records by status.
|  | Step6 | Enter the name of a specific employee in the "Employee Name" field to filter leave records for that employee.
|  | Step7 | Click on Search button
Leave_Admin_10 | Verify Leave List Displayed with Single Leave Status and Date Range | Step1 | Admin Login with Valid Credentials | Confirm that the displayed leave records match the selected filter criteria, including the leave status and date range. | The system should successfully display the leave list based on the selected leave status and date range. | Medium
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Leave List Tab
|  | Step4 | Enter a specific "From Date" to filter leave records based on the starting date.
|  | Step5 | Select a single "Leave Status" filter option
|  | Step6 | Click on Search button
Leave_Admin_11 | Validate Error Message for Insufficient Leave Balance | Step1 | Admin Login with Valid Credentials | Ensure that the system does not allow the submission of the leave request with an insufficient leave balance. | The system should display an error message when a user attempts to request leave with an insufficient leave balance. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Assign Leave Tab
|  | Step4 | Enter the name of a specific employee in the "Employee Name" field
|  | Step5 | Choose a specific "Leave Type"
Leave_Admin_12 | Validate all the employee leave should be shown as per leave type, location and subtype is selected. | Step1 | Admin Login with Valid Credentials | Confirm that the displayed leave records match the selected filter criteria, including leave type, location, and subtype. | The system should successfully display all employee leave records based on the selected filter criteria, including leave type, location, and subtype. | Medium
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Reports menu list and select Leave Entitlements and Usage Report item
|  | Step4 | Choose a specific "Leave Type"
|  | Step5 | Choose a particular "Location"
|  | Step6 | Specify a "Subtype"
|  | Step7 | Click on Generate button
Leave_Admin_13 | Validate all the employee leave should be shown as per leave type and location is selected. | Step1 | Admin Login with Valid Credentials | Confirm that the displayed leave records match the selected filter criteria, including leave type and location. | The system should successfully display all employee leave records based on the selected filter criteria, including leave type and location. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Reports menu list and select Leave Entitlements and Usage Report item
|  | Step4 | Choose a specific "Leave Type"
|  | Step5 | Choose a particular "Location"
|  | Step7 | Click on Generate button
Leave_Admin_14 | Validate all the employee leave should be shown as per leave type and location is selected. | Step1 | Admin Login with Valid Credentials | Confirm that the displayed leave records match the selected filter criteria, including leave type and location. | The system should successfully display all employee leave records based on the selected filter criteria, including leave type and location. | Medium
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Reports menu list and select Leave Entitlements and Usage Report item
|  | Step4 | Select Employee checkbox
|  | Step5 | Enter the name of a specific employee in the "Employee Name" field
|  | Step6 | Enter the leave period, including the start date and end date.
|  | Step7 | Click on Generate button
Leave_Employee_1 | Validate New Employee Can Apply for Leave Type with Sufficient Leave Balance. | Step1 | Employee to login with the valid credentials | Confirm that the system successfully processes the leave request without any errors related to insufficient leave balance. | The system should allow the new employee to apply for the selected leave type when their leave balance is greater than 1. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Apply Tab
|  | Step4 | Select Leave type
|  | Step5 | Enter a specific "From Date" to filter leave records based on the starting date.
|  | Step6 | Click on Apply button
Leave_Employee_2 | Validate New Employee Can Apply for Half-Day Leave with Sufficient Leave Balance. | Step1 | Employee to login with the valid credentials | Confirm that the system successfully processes the half-day leave request without any errors related to insufficient leave balance. | The system should allow the new employee to apply for half-day leave when their leave balance is greater than 1. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Apply Tab
|  | Step4 | Select Leave type
|  | Step5 | Enter a specific "From Date" to filter leave records based on the starting date.
|  | Step6 | Select Duration "Half-Day"
|  | Step7 | Click on Apply button
Leave_Employee_3 | Validate New Employee Can Apply for Specific Time-Based Leave with Sufficient Leave Balance. | Step1 | Employee to login with the valid credentials | Confirm that the system successfully processes the specific time-based leave request without any errors related to insufficient leave balance. | The system should allow the new employee to apply for the specific time-based leave type when their leave balance is greater than 1. | High
|  | Step2 | Click on leave tab from the left grid
|  | Step3 | Click on Apply Tab
|  | Step4 | Select Leave type
|  | Step5 | Enter a specific "From Date" to filter leave records based on the starting date.
|  | Step6 | Select Duration "Specific Time"
|  | Step7 | Enter From and To time
|  | Step8 | Click on Apply button

## PIM
TC No | Test Scenario | Test Description | Step Number | Test Step | Validation | Expected Result | Priority
Add_Emp_01 | Add Employe | Verify if the user is able to Add New Employee | Step 1 | Navigate to the OrangeHRM application | A confirmation message stating that the employee has been added should be visible. | Employee should be added successfully and displayed in the employee list. | High
|  |  | Step 2 | Log in using valid credentials.
|  |  | Step 3 | Go to the PIM module.
|  |  | Step 4 | Click on "Add Employee".
|  |  | Step 5 | Enter valid details in all mandatory fields.
|  |  | Step 6 | Click the "Save" button.
Add_Emp_02 |  | Verify if the user is not able to Add Employee if Mandatory Field is missing | Step 1 | Navigate to the OrangeHRM application | System should display an error message indicating the missing mandatory field(s). | Employee should not be added to the list. | High
|  |  | Step 2 | Log in using valid credentials.
|  |  | Step 3 | Go to the PIM module.
|  |  | Step 4 | Click on "Add Employee".
|  |  | Step 5 | Leave one or more mandatory fields empty.
|  |  | Step 6 | Click the "Save" button.
Add_Emp_03 |  | Verify the Uniqueness of Employee ID | Step 1 | Add a new employee with a specific Employee ID. | System should display an error message indicating that the Employee ID is already in use. | Employee should not be added to the list. | High
|  |  | Step 2 | Add another employee with the same Employee ID.
Add_Emp_04 |  | Verify if the Employee is added and kept as disabled the employee should not be able to login | Step 1 | Navigate to "Add Employee". | System should display an error message indicating the employee is disabled | Employee should not be able to login. | High
|  |  | Step 2 | Enter valid details in all mandatory fields.
|  |  | Step 3 | Click on Create Login Details
|  |  | Step 4 | Select the status as Disabled.
|  |  | Step 5 | Click the "Save" button.
Add_Emp_05 |  | Verify if the User is not able to proceed if "Password " and "Confirm Password" are different. | Step 1 | Navigate to "Add Employee". | System should display an error message indicating that the passwords don’t match. | Employee should not be added to the list. | High
|  |  | Step 2 | Enter valid details in all mandatory fields.
|  |  | Step 3 | Click on Create Login Details
|  |  | Step 4 | Add different data in "Password" & "Confirm Password" fields.
|  |  | Step 5 | Click the "Save" button.
Add_Emp_06 |  | Verify if the Employee created is able to login with valid credentials. | Step1 | Navigate to the OrangeHRM application | System should display message as successfully logged in or something. | Employee should be able to login. | High
|  |  | Step2 | Log in using valid credentials.
Edit_Emp_01 | Edit Employee | Verify if the Employee is able to Edit a Single Field of an Employee Record | Step 1 | Navigate to the OrangeHRM application and log in. | A confirmation message indicating the update should be visible. | The edited information should be updated successfully in the employee's list. | High
|  |  | Step 2 | Access the PIM module.
|  |  | Step 3 | Search for an existing employee.
|  |  | Step 4 | Click on the employee's record to access their details.
|  |  | Step 5 | Edit a single field (e.g., "First Name").
|  |  | Step 6 | Click the "Save" button.
Edit_Emp_02 |  | Verifyif the Employee is able to Edit Multiple Fields of an Employee Record | Step 1 | Navigate to the OrangeHRM application and log in. | A confirmation message stating the changes have been saved should appear. | All edited fields should be updated successfully | Medium
|  |  | Step 2 | Access the PIM module.
|  |  | Step 3 | Search and select an existing employee record.
|  |  | Step 4 | Edit multiple fields (e.g., "First Name " and "Last Number").
|  |  | Step 5 | Click the "Save" button.
Edit_Emp_03 |  | Verify if the user is not able to edit the Employee Id which is already taken or exists. | Step 1 | Access the PIM module. | System should display an error message indicating that the Employee Id is already taken or exists. | User should not be able to edit Employee ID. | Medium
|  |  | Step 2 | Search and select an existing employee record.
|  |  | Step 3 | Edit Employee Id with an id which is already taken.
|  |  | Step 4 | Click the "Save" button.
Edit_Emp_04 |  | Verify if the user is able to Edit a Field with Invalid Data or keep it Empty. | Step 1 | Navigate to the OrangeHRM application and log in. | System should display an error message indicating that the field is required | User should not be able to save the edited fields. | Medium
|  |  | Step 2 | Access the PIM module.
|  |  | Step 3 | Search and select an existing employee record.
|  |  | Step 4 | Edit multiple fields (e.g., "First Name " and "Last Number"). Keep this fields empty or blank
|  |  | Step 5 | Click the "Save" button.
Delete_Emp_01 | Delete Employee | Verify if the user is able to Delete a Single Employee Record | Step 1 | Navigate to the OrangeHRM application and log in. | System should display a message as Delete Successful. | The selected employee should be deleted and not displayed in the Employee list | High
|  |  | Step 2 | Access the PIM module.
|  |  | Step 3 | Search for an existing employee.
|  |  | Step 4 | Select the employee's record using the checkbox beside their name.
|  |  | Step 5 | Click the "Delete" button.
|  |  | Step 6 | In confirmation Popup click on "Yes Delete"
Delete_Emp_02 |  | Verify if the user is able to Delete multiple Employees Record | Step 1 | Access the PIM module. | System should display a message as Delete Successful. | The multiple selected employees should be deleted and not displayed in the Employee list | Medium
|  |  | Step 2 | Search and select multiple employee records using the checkboxes.
|  |  | Step 3 | Click the "Delete" button.
|  |  | Step 4 | In confirmation Popup click on "Yes Delete"
Delete_Emp_03 |  | Verify if the user is able to Cancel Deletion Process | Step 1 | Navigate to the OrangeHRM application and log in. |  | The selected employee should not be deleted and should be displayed in the Employee list | Medium
|  |  | Step 2 | Access the PIM module.
|  |  | Step 3 | Search for an existing employee.
|  |  | Step 4 | Select the employee's record using the checkbox beside their name.
|  |  | Step 5 | Click the "Delete" button.
|  |  | Step 6 | In confirmation Popup click on "No Cancel"
Search_Emp_01 | Search Employee | Verify if the user is able to Search employee based on Employee name. | Step 1 | Navigate to the OrangeHRM application | The searched name value should be displayed in First, middle or last name column in Employee list | The Searched employee should be displayed | High
|  |  | Step 2 | Log in using valid credentials.
|  |  | Step 3 | Go to the PIM module.
|  |  | Step 4 | Click on employee name field and enter name
|  |  | Step 5 | Click on search button.
Search_Emp_02 |  | Verify if the user is able to Search employee based on Employee Id. | Step 1 | Navigate to the OrangeHRM application | The searched Id value should be displayed in ID column in Employee list | The Searched employee should be displayed | High
|  |  | Step 2 | Log in using valid credentials.
|  |  | Step 3 | Go to the PIM module.
|  |  | Step 4 | Click on employee Id field and enter Id
|  |  | Step 5 | Click on search button.
Search_Emp_03 |  | Verify if proper message is displayed to the user if no records are found. | Step 1 | Navigate to the OrangeHRM application | The no records found message should be displayed. | No Employees shouls be dispalyed if the searched value does not match any employee. | High
|  |  | Step 2 | Log in using valid credentials.
|  |  | Step 3 | Go to the PIM module.
|  |  | Step 4 | Enter any random data in any field. (ex: name)
|  |  | Step 5 | Click on search button.

## Dashboard
TC No | Test Description | Step Number | Test Step | Validation | Priority
Dashboard_Admin_1 | "Time at Work" should be there | Step 1 | Admin to login with the valid credentials | Time at work widget should be displayed | Medium
|  | Step 2 | Verify "Time at Work" widget should be there
Dashboard_Admin_2 | "My action" should be there | Step 1 | Admin to login with the valid credentials | My action widget should be displayed | Medium
|  | Step 2 | Verify "My action" widget should be there
Dashboard_Admin_3 | "Quick Launch" should be there | Step 1 | Admin to login with the valid credentials | Quick Launch widget should be displayed | Medium
|  | Step 2 | Verify "Quick Launch" widget should be there
Dashboard_Admin_4 | "Buzz Latest Post" should be there | Step 1 | Admin to login with the valid credentials | Buzz Latest Post widget should be displayed | Medium
|  | Step 2 | Verify "Buzz Latest Post" widget should be there
Dashboard_Admin_5 | "Employees on Leave Today" should be there | Step 1 | Admin to login with the valid credentials | Employees on Leave Today widget should be displayed | Medium
|  | Step 2 | Verify "Employees on Leave Today" widget should be there
Dashboard_Admin_6 | "Employee distribution by subunit" should be there | Step 1 | Admin to login with the valid credentials | Employee distribution by subunit widget should be displayed | Medium
|  | Step 2 | Verify "Employee distribution by subunit" widget should be there
Dashboard_Admin_7 | "Employee distribution by location" should be there | Step 1 | Admin to login with the valid credentials | Employee distribution by location widget should be displayed | Medium
|  | Step 2 | Verify "Employee distribution by location" widget should be there
Dashboard_Admin_8 | verify Timesheets to Approve is displayed under my action | Step 1 | Admin to login with the valid credentials | Timesheets to Approve is displayed under my action | Low
|  | Step 2 | verify Timesheets to Approve is displayed under my action
Dashboard_Admin_9 | verify Pending Self Review is displayed under my action | Step 1 | Admin to login with the valid credentials | Pending Self Review is displayed under my action | Low
|  | Step 2 | verify Pending Self Review is displayed under my action
Dashboard_Admin_10 | verify Candidate to Interview is displayed under my action | Step 1 | Admin to login with the valid credentials | Candidate to Interview is displayed under my action | Low
|  | Step 2 | verify Candidate to Interview is displayed under my action
Dashboard_Admin_11 | verify leaves to approve is displayed under my action | Step 1 | Admin to login with the valid credentials | leaves to approve is displayed under my action | Low
|  | Step 2 | verify leaves to approve is displayed under my action
Dashboard_Admin_12 | verify Assign Leave is displayed under Quick launch wizard | Step 1 | Admin to login with the valid credentials | Assign Leave is displayed under Quick launch wizard | Low
|  | Step 2 | verify Assign Leave is displayed under Quick launch wizard
Dashboard_Admin_13 | Verify Leave List is displayed under Quick launch wizard | Step 1 | Admin to login with the valid credentials | Leave List is displayed under Quick launch wizard | Low
|  | Step 2 | Verify Leave List is displayed under Quick launch wizard
Dashboard_Admin_14 | Verify Time Sheet is displayed under Quick launch wizard | Step 1 | Admin to login with the valid credentials | Time Sheet is displayed under Quick launch wizard | Low
|  | Step 2 | Verify Time Sheet is displayed under Quick launch wizard
Dashboard_Admin_15 | Verify Apply leave is displayed under Quick launch wizard | Step 1 | Admin to login with the valid credentials | Apply leave is displayed under Quick launch wizard | Low
|  | Step 2 | Verify Apply leave is displayed under Quick launch wizard
Dashboard_Admin_16 | Verify My Leave is displayed under Quick launch wizard | Step 1 | Admin to login with the valid credentials | My Leave is displayed under Quick launch wizard | Low
|  | Step 2 | Verify My Leave is displayed under Quick launch wizard
Dashboard_Admin_17 | Verify My timesheet is displayed under Quick launch wizard | Step 1 | Admin to login with the valid credentials | My timesheet is displayed under Quick launch wizard | Low
|  | Step 2 | Verify My timesheet is displayed under Quick launch wizard
Dashboard_Admin_18 | Verify username icon is coming at right top banner | Step 1 | Admin to login with the valid credentials | username icon is coming at right top banner | Low
|  | Step 2 | Verify username icon is coming at right top banner
Dashboard_Admin_19 | verify profile icon has Support link | Step 1 | Admin to login with the valid credentials | verify profile icon has Support link | Low
|  | Step 2 | verify profile icon has Support link
Dashboard_Admin_20 | verify profile icon has About link | Step 1 | Admin to login with the valid credentials | verify profile icon has About link | Low
|  | Step 2 | verify profile icon has About link
Dashboard_Admin_21 | verify profile icon has Change Password link | Step 1 | Admin to login with the valid credentials | verify profile icon has Change Password link | Low
|  | Step 2 | verify profile icon has Change Password link
Dashboard_Admin_22 | verify profile icon has logout link | Step 1 | Admin to login with the valid credentials | verify profile icon has logout link | High
|  | Step 2 | verify profile icon has logout link
Dashboard_Admin_23 | Verify Dashbord has leave link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has leave link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has leave link on left side navigation panel.
Dashboard_Admin_24 | Verify Dashbord has time link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has time link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has time link on left side navigation panel.
Dashboard_Admin_25 | Verify Dashbord has My Info link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has My Info link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has My Info link on left side navigation panel.
Dashboard_Admin_26 | Verify Dashbord has directory link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has directory link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has directory link on left side navigation panel.
Dashboard_Admin_27 | Verify Dashbord has Claim link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has Claim link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Claim link on left side navigation panel.
Dashboard_Admin_28 | Verify Dashbord has Buzz link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has Buzz link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Buzz link on left side navigation panel.
Dashboard_Admin_29 | Verify Dashbord has Admin link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has Admin link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Admin link on left side navigation panel.
Dashboard_Admin_30 | Verify Dashbord has PIM link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has PIM link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has PIM link on left side navigation panel.
Dashboard_Admin_31 | Verify Dashbord has Recruitment link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has Recruitment link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Recruitment link on left side navigation panel.
Dashboard_Admin_32 | Verify Dashbord has Performance link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has Performance link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Performance link on left side navigation panel.
Dashboard_Admin_33 | Verify Dashbord has Maintenance link on left side navigation panel. | Step 1 | Admin to login with the valid credentials | Verify Dashbord has Maintenance link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Maintenance link on left side navigation panel.
Dashboard_Employee_1 | "Time at Work" should be there | Step 1 | Employee to login with the valid credentials | Time at work widget should be displayed | Medium
|  | Step 2 | Verify "Time at Work" widget should be there
Dashboard_Employee_2 | "My action" should be there | Step 1 | Employee to login with the valid credentials | My action widget should be displayed | Medium
|  | Step 2 | Verify "My action" widget should be there
Dashboard_Employee_3 | "Quick Launch" should be there | Step 1 | Employee to login with the valid credentials | Quick Launch widget should be displayed | Medium
|  | Step 2 | Verify "Quick Launch" widget should be there
Dashboard_Employee_4 | "Buzz Latest Post" should be there | Step 1 | Employee to login with the valid credentials | Buzz Latest Post widget should be displayed | Medium
|  | Step 2 | Verify "Buzz Latest Post" widget should be there
Dashboard_Employee_5 | "Employees on Leave Today" should be there | Step 1 | Employee to login with the valid credentials | Employees on Leave Today widget should be displayed | Medium
|  | Step 2 | Verify "Employees on Leave Today" widget should be there
|  | Step 3 | Verify all the employee on leave are displayed in this widget
Dashboard_Employee_6 | Verify Apply leave is displayed under Quick launch wizard | Step 1 | Employee to login with the valid credentials | Apply leave is displayed under Quick launch wizard | Low
|  | Step 2 | Verify Apply leave is displayed under Quick launch wizard
Dashboard_Employee_7 | Verify My Leave is displayed under Quick launch wizard | Step 1 | Employee to login with the valid credentials | My Leave is displayed under Quick launch wizard | Low
|  | Step 2 | Verify My Leave is displayed under Quick launch wizard
Dashboard_Employee_8 | Verify My timesheet is displayed under Quick launch wizard | Step 1 | Employee to login with the valid credentials | My timesheet is displayed under Quick launch wizard | Low
|  | Step 2 | Verify My timesheet is displayed under Quick launch wizard
Dashboard_Employee_9 | Verify Dashbord has leave link on left side navigation panel. | Step 1 | Employee to login with the valid credentials | Dashbord has leave link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has leave link on left side navigation panel.
Dashboard_Employee_10 | Verify Dashbord has time link on left side navigation panel. | Step 1 | Employee to login with the valid credentials | Dashbord has time link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has time link on left side navigation panel.
Dashboard_Employee_11 | Verify Dashbord has My Info link on left side navigation panel. | Step 1 | Employee to login with the valid credentials | Dashbord has My Info link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has My Info link on left side navigation panel.
Dashboard_Employee_12 | Verify Dashbord has directory link on left side navigation panel. | Step 1 | Employee to login with the valid credentials | Dashbord has directory link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has directory link on left side navigation panel.
Dashboard_Employee_13 | Verify Dashbord has Claim link on left side navigation panel. | Step 1 | Employee to login with the valid credentials | Dashbord has Claim link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Claim link on left side navigation panel.
Dashboard_Employee_14 | Verify Dashbord has Buzz link on left side navigation panel. | Step 1 | Employee to login with the valid credentials | Dashbord has Claim link on left side navigation panel. | High
|  | Step 2 | Verify Dashbord has Buzz link on left side navigation panel.

## Login
TC No | Test Description | Step Number | Test Step | Validation | Priority
Login_Admin_1 | Verify able to login using valid admin credentials | Step 1 | Admin to login with the valid credentials | able to login using valid admin credentials and land on admin page | High
|  | Step 2 | Verify able to login using valid admin credentials
Login_Admin_1 | Verify not able to login using invalid admin credentials | Step 1 | Admin to login with the invalid credentials | not able to login using invalid admin credentials and get appropriate error message | High
|  | Step 2 | Verify not able to login using invalid admin credentials
Login_Employee_1 | Verify able to login using valid admin credentials | Step 1 | Employeeto login with the valid credentials | able to login using valid admin credentials and land on admin page | High
|  | Step 2 | Verify able to login using valid admin credentials
Login_Employee_1 | Verify not able to login using invalid admin credentials | Step 1 | Employee to login with the invalid credentials | not able to login using invalid admin credentials and get appropriate error message | High
|  | Step 2 | Verify not able to login using invalid admin credentials
Login_ForgotYourPassword | Verify Forgot your password works | Step 1 | Navigate to portal | validate appropriate message is displayed | Medium
|  | Step 2 | Click on Forgot your password
|  | Step 3 | fill username
|  | Step 4 | click onReset password

## Test_Estimation
Orange_Application
Details/Test Scenario Complexity | Low | Medium | High | Abbreviation used in estimation
No of Test Case | 17 | 26 | 40 | Test case Complexity/Additional efforts | Script development in Hrs/Percentage
Script Development for each TC (in hrs) | 4 | 6 | 8 | Low | 4
Total Script development Efforts (in hrs) | 68 | 156 | 320 | Medium | 6
Review (Development + functional team) | 3.4 | 7.8 | 16 | High | 8
Review incorporation | 3.4 | 7.8 | 16 | Review incorporation | 5
Batch Dry Run | 60 |  |  | Review (Development + functional team) | 5
Script development total efforts | 658 |  |  | Framework Modification | 5
Additional Efforts(in Hrs) |  |  |  | Test Batch Dry Run(Single test data, Different environment , CI/CD Integration) | 10
Framework Modification | 33 |  |  | Contingency | 25
Contingency | 165 |  |  | Skill Set - Beginner | 1.5
Total Efforts(in hrs.) | 856 |  |  | Skill Set - Intermittent | 1.25
Total Efforts based on skill competency | 1070 |  |  | Skill Set - Expert | 1
Total Efforts in person(in Day's) | 134
Module | Test Case
Dashboard | 47
Leave | 17
Time and Attendance Module | 15
PIM | 16
Login | 5
Total Test cases | 100

## OrangeHRM_AllTestCases
Test Case Number | Test Case Name | Design Steps | Test Case Description | Expected Result | Automation Scope | Primary Owner | Automation Feasibility | Automation Priority | Complexity | Task Start Date | Task End Date | Status | Comments
Time_Employee_1 | Time and Attendance Module |  | Employee to record Punch In |  |  | Saba | Yes |  | High
Time_Employee_2 | Time and Attendance Module |  | Employee to record Punch Out |  |  | Saba | Yes |  | High
Time_Employee_3 | Time and Attendance Module |  | Employee to view the punching record |  |  | Saba | Yes |  | High
Time_Employee_4 | Time and Attendance Module |  | Employee to Enter/record the time sheet 8 hrs |  |  | Saba | Yes |  | High
Time_Employee_5 | Time and Attendance Module |  | Employee to Enter/record the time sheet more than 24 hrs a day |  |  | Saba | Yes |  | Medium
Time_Employee_6 | Time and Attendance Module |  | Employee to Enter/record the time sheet less than 0 hrs a day |  |  | Saba | Yes |  | Medium
Time_Admin_1 | Time and Attendance Module |  | Admin to record Punch In |  |  | Saba | Yes |  | Medium
Time_Admin_2 | Time and Attendance Module |  | Admin to record Punch Out |  |  | Saba | Yes |  | Medium
Time_Admin_3 | Time and Attendance Module |  | Admin to view the punching record |  |  | Saba | Yes |  | Medium
Time_Admin_4 | Time and Attendance Module |  | Admin to view the employee record |  |  | Saba | Yes |  | High
Time_Admin_5 | Time and Attendance Module |  | Admin to Enter/record the time sheet for him |  |  | Saba | Yes |  | Medium
Time_Admin_6 | Time and Attendance Module |  | Admin to Enter/record the time sheet for Employee |  |  | Saba | Yes |  | High
Time_Admin_7 | Time and Attendance Module |  | Admin Reporting:Project Report |  |  | Saba | Yes |  | High
Time_Admin_8 | Time and Attendance Module |  | Admin Reporting:Employee Report |  |  | Saba | Yes |  | Medium
Time_Admin_9 | Time and Attendance Module |  | Admin Reporting:Attendence Summary Report |  |  | Saba | Yes |  | Medium
Leave_Admin_1 | Leave Module |  | Verify Admin able to assign/allocate leave for a Specific Employee. |  |  | Shweta | Yes |  | High
Leave_Admin_2 | Leave Module |  | Verify Employee Leave Entitlements by Employee Name, Leave Type, and Leave Period |  |  | Shweta | Yes |  | Medium
Leave_Admin_3 | Leave Module |  | Verify Admin Allocating Leave for Multiple Employees |  |  | Shweta | Yes |  | High
Leave_Admin_4 | Leave Module |  | Verify User Can Configure Leave Types |  |  | Shweta | Yes |  | Medium
Leave_Admin_5 | Leave Module |  | Verify User Can Configure Holidays List |  |  | Shweta | Yes |  | Medium
Leave_Admin_6 | Leave Module |  | Verify Leave List Displayed Based on "From Date," "Show Leave with Status," and "Leave Type" Selections |  |  | Shweta | Yes |  | High
Leave_Admin_7 | Leave Module |  | Verify Error Message for Missing "Show Leave with Status" Selection |  |  | Shweta | Yes |  | High
Leave_Admin_8 | Leave Module |  | Verify Leave List Displayed with Multiple Leave Status Filters and Date Range |  |  | Shweta | Yes |  | Medium
Leave_Admin_9 | Leave Module |  | Verify Employee Leave List Filtered by Name, Leave Status, and Date Range |  |  | Shweta | Yes |  | High
Leave_Admin_10 | Leave Module |  | Verify Leave List Displayed with Single Leave Status and Date Range |  |  | Shweta | Yes |  | Medium
Leave_Admin_11 | Leave Module |  | Validate Error Message for Insufficient Leave Balance |  |  | Shweta | Yes |  | High
Leave_Admin_12 | Leave Module |  | Validate all the employee leave should be shown as per leave type, location and subtype is selected. |  |  | Shweta | Yes |  | Medium
Leave_Admin_13 | Leave Module |  | Validate all the employee leave should be shown as per leave type and location is selected. |  |  | Shweta | Yes |  | High
Leave_Admin_14 | Leave Module |  | Validate all the employee leave should be shown as per leave type and location is selected. |  |  | Shweta | Yes |  | Medium
Leave_Employee_1 | Leave Module |  | Validate New Employee Can Apply for Leave Type with Sufficient Leave Balance. |  |  | Shweta | Yes |  | High
Leave_Employee_2 | Leave Module |  | Validate New Employee Can Apply for Half-Day Leave with Sufficient Leave Balance. |  |  | Shweta | Yes |  | High
Leave_Employee_3 | Leave Module |  | Validate New Employee Can Apply for Specific Time-Based Leave with Sufficient Leave Balance. |  |  | Shweta | Yes |  | High
Add_Employee_01 | PIM |  | Verify if the user is able to Add New Employee |  |  | Siddhant | Yes |  | High
Add_Employee_02 | PIM |  | Verify if the user is not able to Add Employee if Mandatory Field is missing |  |  | Siddhant | Yes |  | High
Add_Employee_03 | PIM |  | Verify the Uniqueness of Employee ID |  |  | Siddhant | Yes |  | High
Add_Employee_04 | PIM |  | Verify if the Employee is added and kept as disabled the employee should not be able to login |  |  | Siddhant | Yes |  | High
Add_Employee_05 | PIM |  | Verify if the User is not able to proceed if "Password " and "Confirm Password" are different. |  |  | Siddhant | Yes |  | High
Add_Employee_06 | PIM |  | Verify if the Employee created is able to login with valid credentials. |  |  | Siddhant | Yes |  | High
Edit_Employee_01 | PIM |  | Verify if the Employee is able to Edit a Single Field of an Employee Record |  |  | Siddhant | Yes |  | High
Edit_Employee_02 | PIM |  | Verifyif the Employee is able to Edit Multiple Fields of an Employee Record |  |  | Siddhant | Yes |  | Medium
Edit_Employee_03 | PIM |  | Verify if the user is not able to edit the Employee Id which is already taken or exists. |  |  | Siddhant | Yes |  | Medium
Edit_Employee_04 | PIM |  | Verify if the user is able to Edit a Field with Invalid Data or keep it Empty. |  |  | Siddhant | Yes |  | Medium
Delete_Employee_01 | PIM |  | Verify if the user is able to Delete a Single Employee Record |  |  | Siddhant | Yes |  | High
Delete_Employee_02 | PIM |  | Verify if the user is able to Delete multiple Employees Record |  |  | Siddhant | Yes |  | Medium
Delete_Employee_03 | PIM |  | Verify if the user is able to Cancel Deletion Process |  |  | Siddhant | Yes |  | Medium
Search_Employee_01 | PIM |  | Verify if the user is able to Search employee based on Employee name. |  |  | Siddhant | Yes |  | High
Search_Employee_02 | PIM |  | Verify if the user is able to Search employee based on Employee Id. |  |  | Siddhant | Yes |  | High
Search_Employee_03 | PIM |  | Verify if proper message is displayed to the user if no records are found. |  |  | Siddhant | Yes |  | High
Dashboard_Admin_1 | Dashboard Module |  | "Time at Work" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Admin_2 | Dashboard Module |  | "My action" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Admin_3 | Dashboard Module |  | "Quick Launch" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Admin_4 | Dashboard Module |  | "Buzz Latest Post" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Admin_5 | Dashboard Module |  | "Employees on Leave Today" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Admin_6 | Dashboard Module |  | "Employee distribution by subunit" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Admin_7 | Dashboard Module |  | "Employee distribution by location" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Admin_8 | Dashboard Module |  | verify Timesheets to Approve is displayed under my action |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_9 | Dashboard Module |  | verify Pending Self Review is displayed under my action |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_10 | Dashboard Module |  | verify Candidate to Interview is displayed under my action |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_11 | Dashboard Module |  | verify leaves to approve is displayed under my action |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_12 | Dashboard Module |  | verify Assign Leave is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_13 | Dashboard Module |  | Verify Leave List is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_14 | Dashboard Module |  | Verify Time Sheet is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_15 | Dashboard Module |  | Verify Apply leave is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_16 | Dashboard Module |  | Verify My Leave is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_17 | Dashboard Module |  | Verify My timesheet is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_18 | Dashboard Module |  | Verify username icon is coming at right top banner |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_19 | Dashboard Module |  | verify profile icon has Support link |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_20 | Dashboard Module |  | verify profile icon has About link |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_21 | Dashboard Module |  | verify profile icon has Change Password link |  |  | Pulkit | Yes |  | Low
Dashboard_Admin_22 | Dashboard Module |  | verify profile icon has logout link |  |  | Pulkit | Yes |  | High
Dashboard_Admin_23 | Dashboard Module |  | Verify Dashbord has leave link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_24 | Dashboard Module |  | Verify Dashbord has time link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_25 | Dashboard Module |  | Verify Dashbord has My Info link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_26 | Dashboard Module |  | Verify Dashbord has directory link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_27 | Dashboard Module |  | Verify Dashbord has Claim link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_28 | Dashboard Module |  | Verify Dashbord has Buzz link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_29 | Dashboard Module |  | Verify Dashbord has Admin link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_30 | Dashboard Module |  | Verify Dashbord has PIM link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_31 | Dashboard Module |  | Verify Dashbord has Recruitment link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_32 | Dashboard Module |  | Verify Dashbord has Performance link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Admin_33 | Dashboard Module |  | Verify Dashbord has Maintenance link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Employee_1 | Dashboard Module |  | "Time at Work" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Employee_2 | Dashboard Module |  | "My action" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Employee_3 | Dashboard Module |  | "Quick Launch" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Employee_4 | Dashboard Module |  | "Buzz Latest Post" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Employee_5 | Dashboard Module |  | "Employees on Leave Today" should be there |  |  | Pulkit | Yes |  | Medium
Dashboard_Employee_6 | Dashboard Module |  | Verify Apply leave is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Employee_7 | Dashboard Module |  | Verify My Leave is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Employee_8 | Dashboard Module |  | Verify My timesheet is displayed under Quick launch wizard |  |  | Pulkit | Yes |  | Low
Dashboard_Employee_9 | Dashboard Module |  | Verify Dashbord has leave link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Employee_10 | Dashboard Module |  | Verify Dashbord has time link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Employee_11 | Dashboard Module |  | Verify Dashbord has My Info link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Employee_12 | Dashboard Module |  | Verify Dashbord has directory link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Employee_13 | Dashboard Module |  | Verify Dashbord has Claim link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Dashboard_Employee_14 | Dashboard Module |  | Verify Dashbord has Buzz link on left side navigation panel. |  |  | Pulkit | Yes |  | High
Login_Admin_1 | Login Module |  | Verify able to login using valid admin credentials |  |  | Pulkit | Yes |  | High
Login_Admin_1 | Login Module |  | Verify not able to login using invalid admin credentials |  |  | Pulkit | Yes |  | High
Login_Employee_1 | Login Module |  | Verify able to login using valid admin credentials |  |  | Pulkit | Yes |  | High
Login_Employee_1 | Login Module |  | Verify not able to login using invalid admin credentials |  |  | Pulkit | Yes |  | High
Login_ForgotYourPassword | Login Module |  | Verify Forgot your password works |  |  | Pulkit | Yes |  | Medium